## Requirements Register
AI Sizing Platform - Source Requirements Register v0.1
Initial controlled baseline. Architecture and backlog documents must be derived from approved requirements in this register.
Requirement ID | Domain | Capability | Requirement Statement | Business Rationale | Classification | Source ID | Source Statement / Decision | Priority | Status | Mandatory? | User Role | Input / Trigger | Derived / Output | Rule / Formula Impact | Catalog / Evidence Impact | Dev Impact | Production Impact | BOM / Financial Impact | Validation / Acceptance Summary | Conflict / Supersession | Open Decision ID | Target Release | Notes
BR-PROD-001 | Product | Purpose | The system shall convert business AI workload requirements into explainable model, infrastructure, cluster, BOM and financial recommendations. | Defines the product outcome. | Approved requirement | SRC-001 | Enterprise AI infrastructure sizing and commercial planning platform. | Must | Proposed | Yes | Product owner |  | Model, infrastructure, BOM and financial recommendations | [8 empty] | R1
BR-PROD-002 | Product | Determinism | The system shall not randomly select any model, precision, runtime, GPU, server, cloud resource, BOM component or price. | Recommendations must be reproducible and defensible. | Approved requirement | SRC-001;SRC-002 | No random or unsupported recommendations. | Must | Proposed | Yes | Product owner |  |  | Eligibility first, then versioned optimization |  |  |  |  | Same snapshot must reproduce identical outputs |  |  | R1
BR-PROD-003 | Product | AI boundary | AI assistance may structure inputs and explain results, but final calculations and recommendations shall come from deterministic rules and governed catalogs. | Prevents opaque AI reasoning from owning procurement decisions. | Approved requirement | SRC-001;SRC-002 | Use rule-based calculation and stored catalog data. | Must | Proposed | Yes | Product owner | [7 empty] | Recommendation works without generative AI availability |  |  | R1
BR-PROD-004 | Product | Readiness | The system shall distinguish Incomplete, Review Required, Planning Estimate, Architecture Ready, Quote Required and Procurement Ready. | Prevents planning outputs being mistaken for purchase instructions. | Approved requirement | SRC-001 | Readiness boundary must be explicit. | Must | Proposed | Yes | Product owner |  | Readiness status and missing actions | [5 empty] | Procurement Ready blocked until mandatory technical and commercial evidence is complete |  |  | R3
BR-PROD-005 | Product | Evidence | The system shall label every material value as measured, catalog-sourced, derived, overridden or approximate. | Builds confidence and exposes uncertainty. | Approved requirement | SRC-002 | Evidence-backed, traceable and clearly labelled approximations. | Must | Proposed | Yes | Product owner |  |  |  | Evidence metadata and confidence |  |  |  | Every recommendation has evidence status |  |  | R1
BR-PROD-006 | Product | Multi-workload | The system shall support multiple applications and multiple use cases in one project. | Enterprise deployments contain multiple workloads. | Approved requirement | SRC-001;SRC-002 | Multiple applications/workloads selected by industry and use case. | Must | Proposed | Yes | Product owner |  | Workload list and consolidated architecture | [8 empty] | R1
BR-PROD-007 | Product | Excel role | The existing workbook shall be treated as a requirements and regression reference, not as the application architecture or automatic source of truth. | Known spreadsheet defects must not be copied. | Business decision | SRC-001;SRC-003 | Workbook is implementation reference, not automatically correct. | Must | Proposed | Yes | Product owner | [7 empty] | Import rejects formula errors, sentinel values and unsupported assumptions |  |  | R1
FR-PRJ-001 | Project | Create project | The landing page shall allow a user to create a new project. | Starts the planning workflow. | Approved requirement | SRC-001 | Landing page create project option. | Must | Proposed | Yes | Executive / Scenario editor | Project name and owner | Draft project | [8 empty] | R1
FR-PRJ-002 | Project | Import project | The landing page shall allow controlled import of a saved project. | Supports reuse and migration. | Approved requirement | SRC-001 | Import saved project option. | Must | Proposed | Yes | Scenario editor | Supported project file | Import report and draft project | [5 empty] | Accepted, defaulted, corrected and rejected fields reported |  |  | R2
FR-PRJ-003 | Project | Scenario versioning | The system shall support saving, cloning, comparing and versioning scenarios. | Enables controlled what-if analysis. | Approved requirement | SRC-002 | Scenario and override traceability. | Must | Proposed | Yes | Product owner |  | Immutable scenario versions | [8 empty] | R1
FR-INP-001 | Inputs | Minimal executive inputs | The primary input journey shall request the minimum business information needed and derive technical values wherever reliable telemetry, governed rules or catalogs exist. | Executives should not enter low-level AI infrastructure values. | Approved requirement | SRC-001;SRC-005 | Minimal executive inputs; classifications require refinement. | Must | Proposed | Yes | Executive |  |  | M/O/D/A/T/C classification |  |  |  |  | Technical fields not shown as mandatory executive fields |  |  | R1
FR-INP-002 | Inputs | Industry | The system shall capture or derive Industry according to source type M. | Controls applicable use cases and governed requirements | Approved requirement | SRC-001;SRC-002;SRC-005 | Always | Must | Proposed | Yes | Executive / Application owner | Industry |  | Source type M |  |  |  |  | Always |  |  | R1
FR-INP-003 | Inputs | Application and multiple use cases | The system shall capture or derive Application and multiple use cases according to source type M. | Defines business workloads | Approved requirement | SRC-001;SRC-002;SRC-005 | Always | Must | Proposed | Yes | Executive / Application owner | Application and multiple use cases |  | Source type M |  |  |  |  | Always |  |  | R1
FR-INP-004 | Inputs | Use-case distribution | The system shall capture or derive Use-case distribution according to source type M. | Distributes common demand without duplication | Approved requirement | SRC-001;SRC-002;SRC-005 | When demand is shared | Must | Proposed | Yes | Executive / Application owner | Use-case distribution |  | Source type M |  |  |  |  | When demand is shared |  |  | R1
FR-INP-005 | Inputs | Applicable demand value | The system shall capture or derive Applicable demand value according to source type M. | Quantifies workload volume | Approved requirement | SRC-001;SRC-002;SRC-005 | Always | Must | Proposed | Yes | Executive / Application owner | Applicable demand value |  | Source type M |  |  |  |  | Always |  |  | R1
FR-INP-006 | Inputs | Demand unit | The system shall capture or derive Demand unit according to source type A/D. | Ensures workload-specific conversion | Approved requirement | SRC-001;SRC-002;SRC-005 | Derived from use case; selectable when multiple units apply | Must | Proposed | Yes | Executive / Application owner | Demand unit |  | Source type A/D |  |  |  |  | Derived from use case; selectable when multiple units apply |  |  | R1
FR-INP-007 | Inputs | Simple/Medium/Complex mix | The system shall capture or derive Simple/Medium/Complex mix according to source type M. | Creates governed request profile | Approved requirement | SRC-001;SRC-002;SRC-005 | Must total 100% | Must | Proposed | Yes | Executive / Application owner | Simple/Medium/Complex mix |  | Source type M |  |  |  |  | Must total 100% |  |  | R1
FR-INP-008 | Inputs | Language coverage | The system shall capture or derive Language coverage according to source type M. | Controls model eligibility and tokenization | Approved requirement | SRC-001;SRC-002;SRC-005 | Always | Must | Proposed | Yes | Executive / Application owner | Language coverage |  | Source type M |  |  |  |  | Always |  |  | R1
FR-INP-009 | Inputs | File types and modality | The system shall capture or derive File types and modality according to source type M. | Controls model, ingestion and storage requirements | Approved requirement | SRC-001;SRC-002;SRC-005 | Always | Must | Proposed | Yes | Executive / Application owner | File types and modality |  | Source type M |  |  |  |  | Always |  |  | R1
FR-INP-010 | Inputs | Availability requirement | The system shall capture or derive Availability requirement according to source type M. | Controls production resilience | Approved requirement | SRC-001;SRC-002;SRC-005 | Always | Must | Proposed | Yes | Executive / Application owner | Availability requirement |  | Source type M |  |  |  |  | Always |  |  | R1
FR-INP-011 | Inputs | DR requirement | The system shall capture or derive DR requirement according to source type M. | Controls recovery capacity and data protection | Approved requirement | SRC-001;SRC-002;SRC-005 | Always | Must | Proposed | Yes | Executive / Application owner | DR requirement |  | Source type M |  |  |  |  | Always |  |  | R1
FR-INP-012 | Inputs | Planning period | The system shall capture or derive Planning period according to source type M. | Controls growth and TCO | Approved requirement | SRC-001;SRC-002;SRC-005 | Always | Must | Proposed | Yes | Executive / Application owner | Planning period |  | Source type M |  |  |  |  | Always |  |  | R1
FR-INP-013 | Inputs | Annual workload growth | The system shall capture or derive Annual workload growth according to source type O. | Projects demand | Approved requirement | SRC-001;SRC-002;SRC-005 | 20% governed default, overrideable | Must | Proposed | Yes | Executive / Application owner | Annual workload growth |  | Source type O |  |  |  |  | 20% governed default, overrideable |  |  | R1
FR-INP-014 | Inputs | Annual data growth | The system shall capture or derive Annual data growth according to source type O. | Projects storage demand | Approved requirement | SRC-001;SRC-002;SRC-005 | 20% governed default, overrideable | Must | Proposed | Yes | Executive / Application owner | Annual data growth |  | Source type O |  |  |  |  | 20% governed default, overrideable |  |  | R1
FR-INP-015 | Inputs | Knowledge volume or tier | The system shall capture or derive Knowledge volume or tier according to source type C. | Sizes RAG storage independently of model size | Approved requirement | SRC-001;SRC-002;SRC-005 | RAG/document workloads | Must | Proposed | Yes | Executive / Application owner | Knowledge volume or tier |  | Source type C |  |  |  |  | RAG/document workloads |  |  | R1
FR-INP-016 | Inputs | Development required | The system shall capture or derive Development required according to source type M. | Determines Development environment | Approved requirement | SRC-001;SRC-002;SRC-005 | Per workload | Must | Proposed | Yes | Executive / Application owner | Development required |  | Source type M |  |  |  |  | Per workload |  |  | R1
FR-INP-017 | Inputs | Production required | The system shall capture or derive Production required according to source type M. | Determines Production environment | Approved requirement | SRC-001;SRC-002;SRC-005 | Per workload | Must | Proposed | Yes | Executive / Application owner | Production required |  | Source type M |  |  |  |  | Per workload |  |  | R1
FR-INP-018 | Inputs | Peak concurrent sessions | The system shall capture or derive Peak concurrent sessions according to source type C/O. | Supports interactive workloads | Approved requirement | SRC-001;SRC-002;SRC-005 | Applicable interactive use cases | Must | Proposed | Yes | Executive / Application owner | Peak concurrent sessions |  | Source type C/O |  |  |  |  | Applicable interactive use cases |  |  | R1
FR-INP-019 | Inputs | Performance requirement tier | The system shall capture or derive Performance requirement tier according to source type M. | Derives latency targets unless custom constraints are entered | Approved requirement | SRC-001;SRC-002;SRC-005 | Per workload | Must | Proposed | Yes | Executive / Application owner | Performance requirement tier |  | Source type M |  |  |  |  | Per workload |  |  | R1
FR-INP-020 | Inputs | RTO and RPO | The system shall capture or derive RTO and RPO according to source type C. | Derives DR pattern | Approved requirement | SRC-001;SRC-002;SRC-005 | When DR is required | Must | Proposed | Yes | Executive / Application owner | RTO and RPO |  | Source type C |  |  |  |  | When DR is required |  |  | R1
FR-INP-021 | Inputs | Deployment preference | The system shall capture or derive Deployment preference according to source type M. | Constrains on-premises, cloud, hybrid or compare-all path | Approved requirement | SRC-001;SRC-002;SRC-005 | Project level | Must | Proposed | Yes | Executive / Application owner | Deployment preference |  | Source type M |  |  |  |  | Project level |  |  | R1
FR-INP-022 | Inputs | Cloud provider and region | The system shall capture or derive Cloud provider and region according to source type C. | Controls availability, residency and pricing | Approved requirement | SRC-001;SRC-002;SRC-005 | Cloud or hybrid | Must | Proposed | Yes | Executive / Application owner | Cloud provider and region |  | Source type C |  |  |  |  | Cloud or hybrid |  |  | R1
FR-INP-023 | Inputs | Security classification and data residency | The system shall capture or derive Security classification and data residency according to source type M/C. | Controls isolation and deployment eligibility | Approved requirement | SRC-001;SRC-002;SRC-005 | Classification mandatory; residency if applicable | Must | Proposed | Yes | Executive / Application owner | Security classification and data residency |  | Source type M/C |  |  |  |  | Classification mandatory; residency if applicable |  |  | R1
FR-INP-024 | Inputs | Budget constraint | The system shall capture or derive Budget constraint according to source type O. | Adds commercial constraint without changing technical demand | Approved requirement | SRC-001;SRC-002;SRC-005 | Project level | Must | Proposed | Yes | Executive / Application owner | Budget constraint |  | Source type O |  |  |  |  | Project level |  |  | R1
FR-INP-025 | Inputs | GPU/server vendor preferences | The system shall capture or derive GPU/server vendor preferences according to source type O. | Filters eligible choices only | Approved requirement | SRC-001;SRC-002;SRC-005 | Project level | Must | Proposed | Yes | Executive / Application owner | GPU/server vendor preferences |  | Source type O |  |  |  |  | Project level |  |  | R1
FR-MOD-001 | Model Selection | Decision matrix | The system shall use a deterministic, evidence-backed model decision matrix for any supported use case. | Model selection must be scalable and explainable. | Approved requirement | SRC-001 | Decision matrix based on industry-accepted baseline. | Must | Proposed | Yes | Product owner |  | Eligible and rejected models |  | Model, use-case, quality and evidence catalogs |  |  |  | Every rejection has a reason |  |  | R2
FR-MOD-002 | Model Selection | Eligibility | The model eligibility gate shall evaluate Industry/use-case compatibility. | Prevents unsupported model recommendations. | Approved requirement | SRC-001;SRC-005 | Industry/use-case compatibility | Must | Proposed | Yes | Product owner |  |  | Hard eligibility constraint | Model/evidence catalogs |  |  |  | Failure makes candidate ineligible |  |  | R2
FR-MOD-003 | Model Selection | Eligibility | The model eligibility gate shall evaluate Task compatibility. | Prevents unsupported model recommendations. | Approved requirement | SRC-001;SRC-005 | Task compatibility | Must | Proposed | Yes | Product owner |  |  | Hard eligibility constraint | Model/evidence catalogs |  |  |  | Failure makes candidate ineligible |  |  | R2
FR-MOD-004 | Model Selection | Eligibility | The model eligibility gate shall evaluate Language compatibility. | Prevents unsupported model recommendations. | Approved requirement | SRC-001;SRC-005 | Language compatibility | Must | Proposed | Yes | Product owner |  |  | Hard eligibility constraint | Model/evidence catalogs |  |  |  | Failure makes candidate ineligible |  |  | R2
FR-MOD-005 | Model Selection | Eligibility | The model eligibility gate shall evaluate Modality compatibility. | Prevents unsupported model recommendations. | Approved requirement | SRC-001;SRC-005 | Modality compatibility | Must | Proposed | Yes | Product owner |  |  | Hard eligibility constraint | Model/evidence catalogs |  |  |  | Failure makes candidate ineligible |  |  | R2
FR-MOD-006 | Model Selection | Eligibility | The model eligibility gate shall evaluate Required context versus supported context. | Prevents unsupported model recommendations. | Approved requirement | SRC-001;SRC-005 | Required context versus supported context | Must | Proposed | Yes | Product owner |  |  | Hard eligibility constraint | Model/evidence catalogs |  |  |  | Failure makes candidate ineligible |  |  | R2
FR-MOD-007 | Model Selection | Eligibility | The model eligibility gate shall evaluate Expected answer compatibility. | Prevents unsupported model recommendations. | Approved requirement | SRC-001;SRC-005 | Expected answer compatibility | Must | Proposed | Yes | Product owner |  |  | Hard eligibility constraint | Model/evidence catalogs |  |  |  | Failure makes candidate ineligible |  |  | R2
FR-MOD-008 | Model Selection | Eligibility | The model eligibility gate shall evaluate Tool/agent capability. | Prevents unsupported model recommendations. | Approved requirement | SRC-001;SRC-005 | Tool/agent capability | Must | Proposed | Yes | Product owner |  |  | Hard eligibility constraint | Model/evidence catalogs |  |  |  | Failure makes candidate ineligible |  |  | R2
FR-MOD-009 | Model Selection | Eligibility | The model eligibility gate shall evaluate Prompt caching support. | Prevents unsupported model recommendations. | Approved requirement | SRC-001;SRC-005 | Prompt caching support | Must | Proposed | Yes | Product owner |  |  | Hard eligibility constraint | Model/evidence catalogs |  |  |  | Failure makes candidate ineligible |  |  | R2
FR-MOD-010 | Model Selection | Eligibility | The model eligibility gate shall evaluate Quality threshold. | Prevents unsupported model recommendations. | Approved requirement | SRC-001;SRC-005 | Quality threshold | Must | Proposed | Yes | Product owner |  |  | Hard eligibility constraint | Model/evidence catalogs |  |  |  | Failure makes candidate ineligible |  |  | R2
FR-MOD-011 | Model Selection | Eligibility | The model eligibility gate shall evaluate License and commercial use. | Prevents unsupported model recommendations. | Approved requirement | SRC-001;SRC-005 | License and commercial use | Must | Proposed | Yes | Product owner |  |  | Hard eligibility constraint | Model/evidence catalogs |  |  |  | Failure makes candidate ineligible |  |  | R2
FR-MOD-012 | Model Selection | Eligibility | The model eligibility gate shall evaluate Deployment compatibility. | Prevents unsupported model recommendations. | Approved requirement | SRC-001;SRC-005 | Deployment compatibility | Must | Proposed | Yes | Product owner |  |  | Hard eligibility constraint | Model/evidence catalogs |  |  |  | Failure makes candidate ineligible |  |  | R2
FR-MOD-013 | Model Selection | Eligibility | The model eligibility gate shall evaluate Runtime compatibility. | Prevents unsupported model recommendations. | Approved requirement | SRC-001;SRC-005 | Runtime compatibility | Must | Proposed | Yes | Product owner |  |  | Hard eligibility constraint | Model/evidence catalogs |  |  |  | Failure makes candidate ineligible |  |  | R2
FR-MOD-014 | Model Selection | Eligibility | The model eligibility gate shall evaluate Precision compatibility. | Prevents unsupported model recommendations. | Approved requirement | SRC-001;SRC-005 | Precision compatibility | Must | Proposed | Yes | Product owner |  |  | Hard eligibility constraint | Model/evidence catalogs |  |  |  | Failure makes candidate ineligible |  |  | R2
FR-MOD-015 | Model Selection | Eligibility | The model eligibility gate shall evaluate Lifecycle and support. | Prevents unsupported model recommendations. | Approved requirement | SRC-001;SRC-005 | Lifecycle and support | Must | Proposed | Yes | Product owner |  |  | Hard eligibility constraint | Model/evidence catalogs |  |  |  | Failure makes candidate ineligible |  |  | R2
FR-MOD-016 | Model Selection | Eligibility | The model eligibility gate shall evaluate Evidence freshness. | Prevents unsupported model recommendations. | Approved requirement | SRC-001;SRC-005 | Evidence freshness | Must | Proposed | Yes | Product owner |  |  | Hard eligibility constraint | Model/evidence catalogs |  |  |  | Failure makes candidate ineligible |  |  | R2
FR-MOD-020 | Model Selection | Performance option | The system shall select and display a Performance-Optimized model from eligible candidates using a versioned objective and tie-break rules. | Provides a performance-prioritized business choice. | Approved requirement | SRC-001 | Performance-Optimized model required. | Must | Proposed | Yes | Product owner |  | Performance-Optimized model and rationale | [5 empty] | Only eligible candidates participate |  |  | R2
FR-MOD-021 | Model Selection | Price option | The system shall select and display a Price-Optimized model based on the lowest projected compliant infrastructure or service cost, not parameter count alone. | Provides a cost-prioritized compliant choice. | Approved requirement | SRC-001 | Price-Optimized model required. | Must | Proposed | Yes | Product owner |  | Price-Optimized model and rationale |  |  |  |  | Planning-period infrastructure cost influences ranking |  |  |  | R2
FR-MOD-022 | Model Selection | Validation checkpoint | Both selected models shall pass a second validation checkpoint before becoming the model baseline. | Reduces unsupported baseline decisions. | Approved requirement | SRC-001 | Validate selected model again. | Must | Proposed | Yes | Product owner |  | Validated model baseline | [5 empty] | Requirement, context, quality, language, modality, license, runtime, precision, evidence, region and lifecycle checks |  |  | R2
FR-MOD-023 | Model Selection | Confidence | The system shall use High, Medium or Low confidence and validated/review statuses rather than claiming absolute 100% confidence. | Evidence can be incomplete or approximate. | Business decision | SRC-001 | Do not use absolute confidence without complete evidence. | Must | Proposed | Yes | Product owner |  | Confidence and readiness | [8 empty] | R2
FR-MOD-024 | Model Selection | Override | After a model recommendation is displayed, an authorized user may override the model with a mandatory reason and automatic downstream recalculation. | Supports customer constraints without losing traceability. | Approved requirement | SRC-002 | Model override must recalculate all affected outputs. | Must | Proposed | Yes | Architect reviewer | Override model and reason | Revised memory, capacity, hardware, HA/DR, BOM and financials | [5 empty] | Hard incompatibilities cannot be bypassed |  |  | R2
FR-GPU-001 | GPU Selection | Checkpoint order | GPU selection shall begin only after a model baseline is validated. | The hardware calculation depends on the selected model. | Approved requirement | SRC-001 | Model checkpoint precedes GPU decision matrix. | Must | Proposed | Yes | Product owner | [10 empty] | R2
FR-GPU-002 | GPU Selection | Decision attribute | The GPU decision matrix shall evaluate Model and architecture. | GPU eligibility and quantity must reflect the complete workload profile. | Approved requirement | SRC-001;SRC-005 | Model and architecture | Must | Proposed | Yes | Product owner |  |  | Derived or catalog-backed decision attribute | Model/runtime/benchmark/hardware/cloud catalogs | [6 empty] | R2
FR-GPU-003 | GPU Selection | Decision attribute | The GPU decision matrix shall evaluate Quantization/precision. | GPU eligibility and quantity must reflect the complete workload profile. | Approved requirement | SRC-001;SRC-005 | Quantization/precision | Must | Proposed | Yes | Product owner |  |  | Derived or catalog-backed decision attribute | Model/runtime/benchmark/hardware/cloud catalogs | [6 empty] | R2
FR-GPU-004 | GPU Selection | Decision attribute | The GPU decision matrix shall evaluate Serving framework and version. | GPU eligibility and quantity must reflect the complete workload profile. | Approved requirement | SRC-001;SRC-005 | Serving framework and version | Must | Proposed | Yes | Product owner |  |  | Derived or catalog-backed decision attribute | Model/runtime/benchmark/hardware/cloud catalogs | [6 empty] | R2
FR-GPU-005 | GPU Selection | Decision attribute | The GPU decision matrix shall evaluate Average and P95 input tokens. | GPU eligibility and quantity must reflect the complete workload profile. | Approved requirement | SRC-001;SRC-005 | Average and P95 input tokens | Must | Proposed | Yes | Product owner |  |  | Derived or catalog-backed decision attribute | Model/runtime/benchmark/hardware/cloud catalogs | [6 empty] | R2
FR-GPU-006 | GPU Selection | Decision attribute | The GPU decision matrix shall evaluate Average and P95 output tokens. | GPU eligibility and quantity must reflect the complete workload profile. | Approved requirement | SRC-001;SRC-005 | Average and P95 output tokens | Must | Proposed | Yes | Product owner |  |  | Derived or catalog-backed decision attribute | Model/runtime/benchmark/hardware/cloud catalogs | [6 empty] | R2
FR-GPU-007 | GPU Selection | Decision attribute | The GPU decision matrix shall evaluate Maximum required context. | GPU eligibility and quantity must reflect the complete workload profile. | Approved requirement | SRC-001;SRC-005 | Maximum required context | Must | Proposed | Yes | Product owner |  |  | Derived or catalog-backed decision attribute | Model/runtime/benchmark/hardware/cloud catalogs | [6 empty] | R2
FR-GPU-008 | GPU Selection | Decision attribute | The GPU decision matrix shall evaluate Peak requests per second. | GPU eligibility and quantity must reflect the complete workload profile. | Approved requirement | SRC-001;SRC-005 | Peak requests per second | Must | Proposed | Yes | Product owner |  |  | Derived or catalog-backed decision attribute | Model/runtime/benchmark/hardware/cloud catalogs | [6 empty] | R2
FR-GPU-009 | GPU Selection | Decision attribute | The GPU decision matrix shall evaluate Peak concurrent requests. | GPU eligibility and quantity must reflect the complete workload profile. | Approved requirement | SRC-001;SRC-005 | Peak concurrent requests | Must | Proposed | Yes | Product owner |  |  | Derived or catalog-backed decision attribute | Model/runtime/benchmark/hardware/cloud catalogs | [6 empty] | R2
FR-GPU-010 | GPU Selection | Decision attribute | The GPU decision matrix shall evaluate P95 TTFT. | GPU eligibility and quantity must reflect the complete workload profile. | Approved requirement | SRC-001;SRC-005 | P95 TTFT | Must | Proposed | Yes | Product owner |  |  | Derived or catalog-backed decision attribute | Model/runtime/benchmark/hardware/cloud catalogs | [6 empty] | R2
FR-GPU-011 | GPU Selection | Decision attribute | The GPU decision matrix shall evaluate P95 TPOT. | GPU eligibility and quantity must reflect the complete workload profile. | Approved requirement | SRC-001;SRC-005 | P95 TPOT | Must | Proposed | Yes | Product owner |  |  | Derived or catalog-backed decision attribute | Model/runtime/benchmark/hardware/cloud catalogs | [6 empty] | R2
FR-GPU-012 | GPU Selection | Decision attribute | The GPU decision matrix shall evaluate Reasoning-effort distribution. | GPU eligibility and quantity must reflect the complete workload profile. | Approved requirement | SRC-001;SRC-005 | Reasoning-effort distribution | Must | Proposed | Yes | Product owner |  |  | Derived or catalog-backed decision attribute | Model/runtime/benchmark/hardware/cloud catalogs | [6 empty] | R2
FR-GPU-013 | GPU Selection | Decision attribute | The GPU decision matrix shall evaluate Workload mix. | GPU eligibility and quantity must reflect the complete workload profile. | Approved requirement | SRC-001;SRC-005 | Workload mix | Must | Proposed | Yes | Product owner |  |  | Derived or catalog-backed decision attribute | Model/runtime/benchmark/hardware/cloud catalogs | [6 empty] | R2
FR-GPU-014 | GPU Selection | Decision attribute | The GPU decision matrix shall evaluate Deployment environment. | GPU eligibility and quantity must reflect the complete workload profile. | Approved requirement | SRC-001;SRC-005 | Deployment environment | Must | Proposed | Yes | Product owner |  |  | Derived or catalog-backed decision attribute | Model/runtime/benchmark/hardware/cloud catalogs | [6 empty] | R2
FR-GPU-015 | GPU Selection | Decision attribute | The GPU decision matrix shall evaluate Cloud provider and region. | GPU eligibility and quantity must reflect the complete workload profile. | Approved requirement | SRC-001;SRC-005 | Cloud provider and region | Must | Proposed | Yes | Product owner |  |  | Derived or catalog-backed decision attribute | Model/runtime/benchmark/hardware/cloud catalogs | [6 empty] | R2
FR-GPU-016 | GPU Selection | Decision attribute | The GPU decision matrix shall evaluate Pricing model. | GPU eligibility and quantity must reflect the complete workload profile. | Approved requirement | SRC-001;SRC-005 | Pricing model | Must | Proposed | Yes | Product owner |  |  | Derived or catalog-backed decision attribute | Model/runtime/benchmark/hardware/cloud catalogs | [6 empty] | R2
FR-GPU-017 | GPU Selection | Decision attribute | The GPU decision matrix shall evaluate Availability and SLA. | GPU eligibility and quantity must reflect the complete workload profile. | Approved requirement | SRC-001;SRC-005 | Availability and SLA | Must | Proposed | Yes | Product owner |  |  | Derived or catalog-backed decision attribute | Model/runtime/benchmark/hardware/cloud catalogs | [6 empty] | R2
FR-GPU-018 | GPU Selection | Decision attribute | The GPU decision matrix shall evaluate Optimization objective. | GPU eligibility and quantity must reflect the complete workload profile. | Approved requirement | SRC-001;SRC-005 | Optimization objective | Must | Proposed | Yes | Product owner |  |  | Derived or catalog-backed decision attribute | Model/runtime/benchmark/hardware/cloud catalogs | [6 empty] | R2
FR-GPU-019 | GPU Selection | Decision attribute | The GPU decision matrix shall evaluate Weight memory. | GPU eligibility and quantity must reflect the complete workload profile. | Approved requirement | SRC-001;SRC-005 | Weight memory | Must | Proposed | Yes | Product owner |  |  | Derived or catalog-backed decision attribute | Model/runtime/benchmark/hardware/cloud catalogs | [6 empty] | R2
FR-GPU-020 | GPU Selection | Decision attribute | The GPU decision matrix shall evaluate KV-cache memory. | GPU eligibility and quantity must reflect the complete workload profile. | Approved requirement | SRC-001;SRC-005 | KV-cache memory | Must | Proposed | Yes | Product owner |  |  | Derived or catalog-backed decision attribute | Model/runtime/benchmark/hardware/cloud catalogs | [6 empty] | R2
FR-GPU-021 | GPU Selection | Decision attribute | The GPU decision matrix shall evaluate Runtime/workspace memory. | GPU eligibility and quantity must reflect the complete workload profile. | Approved requirement | SRC-001;SRC-005 | Runtime/workspace memory | Must | Proposed | Yes | Product owner |  |  | Derived or catalog-backed decision attribute | Model/runtime/benchmark/hardware/cloud catalogs | [6 empty] | R2
FR-GPU-022 | GPU Selection | Decision attribute | The GPU decision matrix shall evaluate Prefill load. | GPU eligibility and quantity must reflect the complete workload profile. | Approved requirement | SRC-001;SRC-005 | Prefill load | Must | Proposed | Yes | Product owner |  |  | Derived or catalog-backed decision attribute | Model/runtime/benchmark/hardware/cloud catalogs | [6 empty] | R2
FR-GPU-023 | GPU Selection | Decision attribute | The GPU decision matrix shall evaluate Decode load. | GPU eligibility and quantity must reflect the complete workload profile. | Approved requirement | SRC-001;SRC-005 | Decode load | Must | Proposed | Yes | Product owner |  |  | Derived or catalog-backed decision attribute | Model/runtime/benchmark/hardware/cloud catalogs | [6 empty] | R2
FR-GPU-024 | GPU Selection | Decision attribute | The GPU decision matrix shall evaluate Memory-driven GPU count. | GPU eligibility and quantity must reflect the complete workload profile. | Approved requirement | SRC-001;SRC-005 | Memory-driven GPU count | Must | Proposed | Yes | Product owner |  |  | Derived or catalog-backed decision attribute | Model/runtime/benchmark/hardware/cloud catalogs | [6 empty] | R2
FR-GPU-025 | GPU Selection | Decision attribute | The GPU decision matrix shall evaluate Throughput-driven GPU count. | GPU eligibility and quantity must reflect the complete workload profile. | Approved requirement | SRC-001;SRC-005 | Throughput-driven GPU count | Must | Proposed | Yes | Product owner |  |  | Derived or catalog-backed decision attribute | Model/runtime/benchmark/hardware/cloud catalogs | [6 empty] | R2
FR-GPU-026 | GPU Selection | Decision attribute | The GPU decision matrix shall evaluate Latency-driven replicas. | GPU eligibility and quantity must reflect the complete workload profile. | Approved requirement | SRC-001;SRC-005 | Latency-driven replicas | Must | Proposed | Yes | Product owner |  |  | Derived or catalog-backed decision attribute | Model/runtime/benchmark/hardware/cloud catalogs | [6 empty] | R2
FR-GPU-027 | GPU Selection | Decision attribute | The GPU decision matrix shall evaluate TP/EP topology. | GPU eligibility and quantity must reflect the complete workload profile. | Approved requirement | SRC-001;SRC-005 | TP/EP topology | Must | Proposed | Yes | Product owner |  |  | Derived or catalog-backed decision attribute | Model/runtime/benchmark/hardware/cloud catalogs | [6 empty] | R2
FR-GPU-028 | GPU Selection | Decision attribute | The GPU decision matrix shall evaluate GPU bandwidth requirement. | GPU eligibility and quantity must reflect the complete workload profile. | Approved requirement | SRC-001;SRC-005 | GPU bandwidth requirement | Must | Proposed | Yes | Product owner |  |  | Derived or catalog-backed decision attribute | Model/runtime/benchmark/hardware/cloud catalogs | [6 empty] | R2
FR-GPU-040 | GPU Selection | Compatibility | The system shall select only GPUs proven compatible with the baselined model, precision, runtime and deployable server or cloud resource. | Prevents arbitrary accelerator choice. | Approved requirement | SRC-001 | GPU compatibility must be catalog driven. | Must | Proposed | Yes | Product owner | [7 empty] | Unsupported combinations are rejected with reason |  |  | R2
FR-GPU-041 | GPU Selection | Performance option | The system shall produce a Performance-Optimized GPU and infrastructure option. | Provides the high-performance alternative. | Approved requirement | SRC-001 | Performance option shown in output BOM and financial page. | Must | Proposed | Yes | Product owner |  | Performance GPU/server/cloud configuration | [8 empty] | R2
FR-GPU-042 | GPU Selection | Price option | The system shall produce the lowest-cost eligible deployable GPU and infrastructure option. | Provides the cost-compliant alternative. | Approved requirement | SRC-001 | Price option shown in output BOM and financial page. | Must | Proposed | Yes | Product owner |  | Price GPU/server/cloud configuration | [8 empty] | R2
FR-CAT-001 | Catalogs | Model catalog | The system shall maintain a governed, versioned Model catalog: Model identity, architecture, language, modality, context, license, lifecycle, precision, runtime and evidence. | Separates controlled evidence from calculations. | Approved requirement | SRC-001;SRC-002 | Model identity, architecture, language, modality, context, license, lifecycle, precision, runtime and evidence. | Must | Proposed | Yes | Catalog steward / approver |  |  |  | Model catalog |  |  |  | Draft records cannot influence production recommendations; active evidence required |  |  | R1
FR-CAT-002 | Catalogs | Use-case and demand catalog | The system shall maintain a governed, versioned Use-case and demand catalog: Industry/use-case mapping, workload type, demand units and conversion rules. | Separates controlled evidence from calculations. | Approved requirement | SRC-001;SRC-002 | Industry/use-case mapping, workload type, demand units and conversion rules. | Must | Proposed | Yes | Catalog steward / approver |  |  |  | Use-case and demand catalog |  |  |  | Draft records cannot influence production recommendations; active evidence required |  |  | R1
FR-CAT-003 | Catalogs | Runtime and precision catalog | The system shall maintain a governed, versioned Runtime and precision catalog: Framework versions, model support, precision support and operational constraints. | Separates controlled evidence from calculations. | Approved requirement | SRC-001;SRC-002 | Framework versions, model support, precision support and operational constraints. | Must | Proposed | Yes | Catalog steward / approver |  |  |  | Runtime and precision catalog |  |  |  | Draft records cannot influence production recommendations; active evidence required |  |  | R1
FR-CAT-004 | Catalogs | Benchmark catalog | The system shall maintain a governed, versioned Benchmark catalog: Matched model, revision, precision, runtime, hardware, parallelism, token lengths, concurrency, TTFT, TPOT and TPS. | Separates controlled evidence from calculations. | Approved requirement | SRC-001;SRC-002 | Matched model, revision, precision, runtime, hardware, parallelism, token lengths, concurrency, TTFT, TPOT and TPS. | Must | Proposed | Yes | Catalog steward / approver |  |  |  | Benchmark catalog |  |  |  | Draft records cannot influence production recommendations; active evidence required |  |  | R1
FR-CAT-005 | Catalogs | Hardware catalog | The system shall maintain a governed, versioned Hardware catalog: GPU, server, complete configuration, lifecycle, compatibility and source evidence. | Separates controlled evidence from calculations. | Approved requirement | SRC-001;SRC-002 | GPU, server, complete configuration, lifecycle, compatibility and source evidence. | Must | Proposed | Yes | Catalog steward / approver |  |  |  | Hardware catalog |  |  |  | Draft records cannot influence production recommendations; active evidence required |  |  | R1
FR-CAT-006 | Catalogs | Cloud catalog | The system shall maintain a governed, versioned Cloud catalog: Provider, region, exact SKU, capabilities, services, billing units and prices. | Separates controlled evidence from calculations. | Approved requirement | SRC-001;SRC-002 | Provider, region, exact SKU, capabilities, services, billing units and prices. | Must | Proposed | Yes | Catalog steward / approver |  |  |  | Cloud catalog |  |  |  | Draft records cannot influence production recommendations; active evidence required |  |  | R1
FR-CAT-007 | Catalogs | Storage/network/software catalogs | The system shall maintain a governed, versioned Storage/network/software catalogs: Deployable shared infrastructure and commercial records. | Separates controlled evidence from calculations. | Approved requirement | SRC-001;SRC-002 | Deployable shared infrastructure and commercial records. | Must | Proposed | Yes | Catalog steward / approver |  |  |  | Storage/network/software catalogs |  |  |  | Draft records cannot influence production recommendations; active evidence required |  |  | R1
FR-CAT-008 | Catalogs | Policy catalog | The system shall maintain a governed, versioned Policy catalog: Growth, utilization, Development, HA, DR, evidence and readiness policies. | Separates controlled evidence from calculations. | Approved requirement | SRC-001;SRC-002 | Growth, utilization, Development, HA, DR, evidence and readiness policies. | Must | Proposed | Yes | Catalog steward / approver |  |  |  | Policy catalog |  |  |  | Draft records cannot influence production recommendations; active evidence required |  |  | R1
FR-CAT-009 | Catalogs | Price catalog | The system shall maintain a governed, versioned Price catalog: Dated, regional, currency-specific prices and quote validity. | Separates controlled evidence from calculations. | Approved requirement | SRC-001;SRC-002 | Dated, regional, currency-specific prices and quote validity. | Must | Proposed | Yes | Catalog steward / approver |  |  |  | Price catalog |  |  |  | Draft records cannot influence production recommendations; active evidence required |  |  | R1
FR-CAL-001 | Calculation | Token engine | The system shall calculate average and percentile input, output, system, history, retrieval, tool and cache token components. | Tokens drive context, memory, capacity and cost. | Approved requirement | SRC-001;SRC-002;SRC-004 | The system shall calculate average and percentile input, output, system, history, retrieval, tool and cache token components. | Must | Proposed | Yes | Product owner |  |  | Versioned formula registry |  |  |  |  | Units, boundaries and evidence recorded |  |  | R2
FR-CAL-002 | Calculation | Memory engine | The system shall calculate weights, quantization metadata, KV cache, runtime workspace, training states, fragmentation and safety reserve as applicable. | Model weights alone are insufficient. | Approved requirement | SRC-001;SRC-002;SRC-004 | The system shall calculate weights, quantization metadata, KV cache, runtime workspace, training states, fragmentation and safety reserve as applicable. | Must | Proposed | Yes | Product owner |  |  | Versioned formula registry |  |  |  |  | Units, boundaries and evidence recorded |  |  | R2
FR-CAL-003 | Calculation | Demand engine | The system shall convert each workload-specific business unit into technical demand using a versioned rule. | Different units require different semantics. | Approved requirement | SRC-001;SRC-002;SRC-004 | The system shall convert each workload-specific business unit into technical demand using a versioned rule. | Must | Proposed | Yes | Product owner |  |  | Versioned formula registry |  |  |  |  | Units, boundaries and evidence recorded |  |  | R2
FR-CAL-004 | Calculation | Inference capacity | The system shall calculate prefill, decode, latency and replica constraints separately. | Input and output behavior differ. | Approved requirement | SRC-001;SRC-002;SRC-004 | The system shall calculate prefill, decode, latency and replica constraints separately. | Must | Proposed | Yes | Product owner |  |  | Versioned formula registry |  |  |  |  | Units, boundaries and evidence recorded |  |  | R2
FR-CAL-005 | Calculation | Training capacity | The system shall distinguish training and fine-tuning methods and calculate compute, memory, scaling efficiency and deadline. | One generic training formula is insufficient. | Approved requirement | SRC-001;SRC-002;SRC-004 | The system shall distinguish training and fine-tuning methods and calculate compute, memory, scaling efficiency and deadline. | Must | Proposed | Yes | Product owner |  |  | Versioned formula registry |  |  |  |  | Units, boundaries and evidence recorded |  |  | R2
FR-CAL-006 | Calculation | Storage | The system shall size knowledge, vector/index, training, checkpoint, logs, backup, archive and DR storage. | Storage is independent of model parameter size. | Approved requirement | SRC-001;SRC-002;SRC-004 | The system shall size knowledge, vector/index, training, checkpoint, logs, backup, archive and DR storage. | Must | Proposed | Yes | Product owner |  |  | Versioned formula registry |  |  |  |  | Units, boundaries and evidence recorded |  |  | R2
FR-CAL-007 | Calculation | Network | The system shall size north-south, east-west, storage, checkpoint, backup and replication traffic and deployable network components. | Fabric and BOM require topology-aware design. | Approved requirement | SRC-001;SRC-002;SRC-004 | The system shall size north-south, east-west, storage, checkpoint, backup and replication traffic and deployable network components. | Must | Proposed | Yes | Product owner |  |  | Versioned formula registry |  |  |  |  | Units, boundaries and evidence recorded |  |  | R2
FR-CLS-001 | Clustering | Dev/Prod separation | The system shall size Development and Production independently. | Development must not automatically inherit Production demand, HA or DR. | Approved requirement | SRC-002 | Separate Development and Production outputs. | Must | Proposed | Yes | Product owner |  |  |  |  | Input-driven Development profile | Full production workload and resilience |  |  |  |  | R3
FR-CLS-002 | Clustering | Compatibility | The system shall consolidate workloads only when environment, runtime, precision, GPU architecture, security, residency, SLA, DR, tenancy and fabric requirements are compatible. | Prevents unsafe sharing. | Approved requirement | SRC-001;SRC-002 | Compatible workloads may share; incompatible remain isolated. | Must | Proposed | Yes | Product owner | [7 empty] | Every pool membership is explainable |  |  | R3
FR-CLS-003 | Clustering | Aggregate before rounding | Compatible concurrent demand shall be aggregated at node-pool level before final GPU/server rounding where technically valid. | Avoids per-workload over-sizing. | Approved requirement | SRC-002;SRC-004 | Pool consolidation before deployable rounding. | Must | Proposed | Yes | Product owner |  |  | Pool demand / utilization / scheduler efficiency, then ceiling | [7 empty] | R3
FR-CLS-004 | Clustering | Allocation modes | The system shall support whole GPU, dedicated GPU/node, supported MIG profiles and approved time slicing. | Improves utilization without compromising isolation. | Approved requirement | SRC-001;SRC-004 | Allocation method must be catalog and policy driven. | Must | Proposed | Yes | Product owner | [10 empty] | R3
FR-HA-001 | Resilience | HA ownership | The system shall apply active failure and maintenance reserve exactly once at the consolidated pool/failure-domain layer. | Prevents duplicate capacity. | Approved requirement | SRC-002;SRC-004 | No double counting of HA. | Must | Proposed | Yes | Product owner | [7 empty] | Reconciliation test proves single application |  |  | R3
FR-DR-001 | Resilience | DR ownership | The system shall derive DR resources from RTO, RPO, recovery priority and topology and apply them exactly once. | Prevents simplistic or duplicated DR. | Approved requirement | SRC-001;SRC-004 | DR compute, storage, network, software and site/region requirements. | Must | Proposed | Yes | Product owner | [10 empty] | R3
FR-BOM-001 | BOM | Complete on-prem BOM | The system shall produce complete configured compute, storage, network, management, software, support, HA and DR BOM lines. | Procurement requires more than GPU names. | Approved requirement | SRC-001;SRC-002 | Full system configuration details required. | Must | Proposed | Yes | Product owner | [6 empty] | Quantity, unit, part/configuration, price, source, date and readiness |  |  |  | R3
FR-BOM-002 | BOM | Shared components | Shared infrastructure shall be counted once per environment, scenario and applicable failure domain. | Prevents double-counting. | Approved requirement | SRC-002 | Consolidated shared BOM. | Must | Proposed | Yes | Product owner | [7 empty] | Detailed and executive totals reconcile |  |  | R3
FR-BOM-003 | BOM | Cloud BOM | Cloud output shall contain provider, region, exact SKU/service, quantity, hours/usage, billing unit, unit price, price date and source. | Generic zero-priced cloud rows are misleading. | Approved requirement | SRC-001;SRC-002 | Proper cloud values required. | Must | Proposed | Yes | Product owner | [7 empty] | Missing record blocks Cloud Procurement Ready |  |  | R4
FR-FIN-001 | Financials | Financial scope | The system shall calculate CAPEX, recurring OPEX, cloud run rate and planning-period TCO from detailed BOM lines. | Executives need transparent financial comparison. | Approved requirement | SRC-001;SRC-002 | Executive BOM and financial landing page. | Must | Proposed | Yes | Product owner | [6 empty] | Compute, storage, network, software, support, services, HA, DR and disclosed exclusions |  |  |  | R3
FR-FIN-002 | Financials | Four options | The output shall show Development Performance-Optimized, Development Price-Optimized, Production Performance-Optimized and Production Price-Optimized. | Separates environment and objective. | Approved requirement | SRC-001;SRC-002 | Performance and Price choices shown for Dev and Production. | Must | Proposed | Yes | Product owner |  | Four clearly named options | [8 empty] | R3
FR-UX-001 | UX | Page 1 | Page 1 shall support create/import project and minimal executive inputs for multiple applications/use cases. | Simple business-facing entry. | Approved requirement | SRC-001 | Landing page and minimal inputs. | Must | Proposed | Yes | Executive / Scenario editor | [10 empty] | R1
FR-UX-002 | UX | Page 2 | Page 2 shall show validation, calculations, model and GPU decision matrices, checkpoints, evidence, confidence and rejected-option reasons. | Users must understand the recommendation. | Approved requirement | SRC-001 | Calculation page. | Must | Proposed | Yes | Product owner |  | Decision and calculation workspace | [8 empty] | R2
FR-UX-003 | UX | Page 3 | Page 3 shall show complete Development and Production BOMs and financial calculations. | Provides the final business decision view. | Approved requirement | SRC-001 | Final BOM and financial page. | Must | Proposed | Yes | Product owner |  | Executive and procurement-oriented output | [8 empty] | R3
FR-UX-004 | UX | Guided and expert modes | The system shall use a guided minimal-input experience with expert drill-down for technical constraints and overrides. | Balances executive simplicity with engineering control. | Approved requirement | SRC-002;SRC-004 | Minimal executive input while retaining expert controls. | Must | Proposed | Yes | Product owner | [10 empty] | R1
FR-TRC-001 | Traceability | End-to-end trace | Every material output shall trace to source inputs, formula/policy version, catalog records, benchmark/price evidence, overrides, status and limitations. | Required for audit and confidence. | Approved requirement | SRC-001;SRC-002 | Full traceability. | Must | Proposed | Yes | Product owner | [7 empty] | Trace reconstructs each result |  |  | R1
FR-TST-001 | Testing | No formula defects | The calculation engine shall prevent circular references, formula errors, unintended double counting, invalid units and non-deployable fractional quantities. | Workbook history demonstrates these risks. | Approved requirement | SRC-003;SRC-004 | Do not copy workbook defects. | Must | Proposed | Yes | Product owner | [7 empty] | Automated invariant and regression tests |  |  | R1
FR-TST-002 | Testing | Sensitivity | Every material input shall have a test proving the intended downstream result changes. | A field that does not affect its intended output is incomplete. | Approved requirement | SRC-002 | Material input sensitivity required. | Must | Proposed | Yes | Product owner | [10 empty] | R2
FR-TST-003 | Testing | Golden scenarios | At least ten diverse end-to-end scenarios shall cover inference, RAG, multimodal, training, fine-tuning, availability, DR, cloud and overrides. | Structural PASS tests are insufficient. | Approved requirement | SRC-002;SRC-004 | Five-cycle and semantic validation. | Must | Proposed | Yes | Product owner | [10 empty] | R2
NFR-SEC-001 | Security | Tenant and access control | The application shall provide enterprise authentication, role-based authorization, tenant isolation, encryption and immutable audit. | Enterprise business data requires strong controls. | Missing requirement | SRC-004 | Identified during web-app planning. | Must | Proposed | Yes | Product owner | [10 empty] | R1
NFR-OPS-001 | Operations | Reproducibility | Each calculation run shall preserve immutable input, formula, policy, catalog, benchmark and price snapshots. | Results must remain reproducible after catalogs change. | Approved requirement | SRC-001;SRC-002 | Versioned and traceable calculations. | Must | Proposed | Yes | Product owner | [10 empty] | R1

## Source Inventory
Source Requirements Register - Source Inventory
Controlled inventory of the sources that will be mined before HLD, LLD, UX, database design, API design, or Agile backlog are approved.
Source ID | Source Type | Source Name | Authority / Owner | Status | Precedence | How Used | Known Limitations | Date Captured | Evidence Location | Notes
SRC-001 | Conversation | Current requirements conversation | Product owner | Active | 1 | Primary approved business decisions and corrections | Contains evolving and superseded statements | 2026-09-21 | Current conversation | Most recent explicit correction takes precedence.
SRC-002 | Saved governance | Persisted AI sizing requirements | Product owner | Active | 2 | Mandatory product, formula, catalog, BOM and workflow rules | Summarized context; must be decomposed | 2026-09-21 | User profile / saved requirements | Must not be silently simplified.
SRC-003 | Workbook | AI_Infrastructure_Sizing_Redesigned_7.6_Fullworking.xlsx | Product owner | Reference only | 4 | Current implementation behavior, formulas, catalogs and defects | Not automatically correct; contains known gaps | 2026-09-21 | Attached workbook | Use as implementation reference and regression source.
SRC-004 | README | README_AI_Infrastructure_Sizing_v8.3_Complete_User_Guide_Roadmap.txt | Product owner | Reference | 3 | Formula glossary, assumptions, missing parts and future checklist | Documents older workbook version | 2026-09-18 | Generated README | Must be reconciled with latest decisions.
SRC-005 | Business matrix | Model/GPU mandatory-input and derivation matrix | Product owner | Active | 1 | Model and GPU checkpoint requirements | Input classifications still require refinement | 2026-09-21 | Current conversation | M/O/D/A/C/T classifications.
SRC-006 | Withdrawn draft | AI_Sizing_Platform_HLD_v1.0.docx | Assistant draft | Withdrawn | 9 | May reveal topics only | Generic and incomplete; must not be treated as approved | 2026-09-21 | Prior output | Do not reuse as source of approved requirements.
SRC-007 | Withdrawn draft | AI_Sizing_Platform_LLD_v1.0.docx | Assistant draft | Withdrawn | 9 | May reveal topics only | Not implementation-ready | 2026-09-21 | Prior output | Do not reuse as source of approved requirements.
SRC-008 | Withdrawn draft | AI_Sizing_Platform_Agile_User_Stories_v1.0.docx | Assistant draft | Withdrawn | 9 | May reveal topics only | Not traceable to complete baseline | 2026-09-21 | Prior output | Do not reuse as approved backlog.
SRC-009 | External evidence | Authoritative standards/vendor/benchmark/cloud sources | Respective publishers | Future collection | 5 | Validate formulas, compatibility, benchmarks, security and prices | Must be current, matched and traceable | TBD | Evidence repository | Planning assumptions allowed only when clearly labelled.

## Decision Log
Decision Log
Approved and proposed business decisions separated from implementation assumptions.
Decision ID | Domain | Decision | Rationale | Status | Source ID | Decision Owner | Date | Impact | Supersedes
DEC-001 | Delivery method | Requirements baseline must be approved before HLD, LLD or Agile backlog. | Prevents omissions and generic architecture. | Approved | SRC-001 | Product owner | 2026-09-21 | All architecture and delivery artifacts | Prior generic documents
DEC-002 | Recommendation | Eligibility shall be evaluated before optimization. | Cost or performance ranking must not include incompatible options. | Approved | SRC-001 | Product owner | 2026-09-21 | Model/GPU/server/cloud engines
DEC-003 | User experience | Use three principal pages with controlled drill-downs. | Keeps executive flow simple. | Approved | SRC-001 | Product owner | 2026-09-21 | UX information architecture
DEC-004 | Confidence | Do not claim absolute 100% confidence; display validation and evidence confidence. | Real-world evidence can be incomplete. | Proposed | SRC-001 | Product owner | 2026-09-21 | Recommendation status model
DEC-005 | Input model | Add T for telemetry-preferred inputs to M/O/D/A/C legend. | Average tokens and RPS ideally come from telemetry. | Proposed | SRC-001 | Product owner | 2026-09-21 | Input dictionary

## Open Decisions
Open Decisions
Items requiring evidence or explicit product-owner approval. These do not block source capture.
Open Decision ID | Domain | Question | Why It Matters | Options / Inputs Needed | Recommendation for Resolution | Owner | Priority | Target Domain Review | Status | Related Requirements
OD-001 | Inputs | Approve T as a formal source classification? | Distinguishes telemetry from manual and derived values. | Use T or retain M/D only. | Adopt T with fallback behavior. | Product owner | High | Input dictionary | Open | FR-INP-001
OD-002 | Model Selection | What governed quality metrics and weights apply by use case? | Performance model ranking needs objective evidence. | Task-specific benchmark policy. | Define per-use-case scorecards; no universal weights. | AI architecture owner | High | Model decision matrix | Open | FR-MOD-020
OD-003 | Development | How shall Development demand be derived? | Hardcoded 15% is invalid as universal policy. | Developer/experiment inputs, governed tiers, telemetry. | Use input-driven profile with governed fallback tier. | Product owner | High | Inputs and clustering | Open | FR-CLS-001
OD-004 | Clustering | How shall workload peak overlap be represented? | Determines pool capacity. | Schedules, telemetry, governed coincidence classes. | Prefer schedules/telemetry; fallback conservative 1.0. | Platform architect | High | Cluster design | Open | FR-CLS-003
OD-005 | Resilience | What failure-reserve policy replaces generic multipliers? | Determines true N+1/N+2 capacity. | Node-pool and failure-domain policies. | Define active + maintenance + explicit failure reserve. | Reliability architect | High | HA/DR | Open | FR-HA-001
OD-006 | Readiness | What exact gates produce Procurement Ready? | Prevents unsupported purchasing. | Technical, evidence, quote and approval checklist. | Define mandatory gates per deployment path. | Procurement owner | High | BOM and financials | Open | BR-PROD-004
OD-007 | Cloud | Which pricing models are mandatory in MVP? | Cloud comparison scope affects data model. | On-demand only versus on-demand plus committed. | MVP: on-demand plus one commitment option per provider if evidence exists. | Cloud/FinOps owner | Medium | Cloud catalog | Open | FR-CAT-006

## Input Baseline
Initial Input Baseline
First-pass field inventory. Full field-by-field data dictionary will be derived after this register is approved.
Input ID | Level | Display Name | Source Type | Mandatory Condition | Default | Allowed Values / Unit | Business Meaning | Why Required | Derived From | Impacts | Missing-Data Behavior | Status
INP-001 | Project | Project Name | M | Always |  | Text | Project identifier | Organizes scenarios |  | Project records and reports | Block creation | Proposed
INP-002 | Project | Industry | M | Always |  | Governed list | Business domain | Controls use-case mapping |  | Use cases, policies and evidence | Block calculation | Proposed
INP-003 | Project | Deployment Preference | M | Always | Compare All | On-Premises / Cloud / Hybrid / Compare All | Deployment path | Controls candidate catalogs |  | BOM and financial paths | Block calculation | Proposed
INP-004 | Project | Planning Period | M | Always | 3 years | 1-10 years | Planning horizon | Growth and TCO |  | Demand, storage and TCO | Block calculation | Proposed
INP-005 | Project | Availability Requirement | M | Always |  | Governed availability levels | Service continuity requirement | Derives failure reserve |  | Production capacity and BOM | Block Production calculation | Proposed
INP-006 | Project | DR Requirement | M | Always |  | Governed DR levels | Recovery strategy | Defines recovery resources |  | DR compute/storage/network/software | Block Production readiness | Proposed
INP-007 | Project | Annual Workload Growth | O | Always | 20% | 0-100% governed range | Demand growth | Projects workload demand |  | Capacity and TCO | Use labelled default | Proposed
INP-008 | Project | Annual Data Growth | O | Always | 20% | 0-100% governed range | Data growth | Projects storage demand |  | Storage and TCO | Use labelled default | Proposed
INP-009 | Workload | Application Name | M | Per workload |  | Text | Application grouping | Groups multiple use cases |  | Navigation and allocation | Block workload | Proposed
INP-010 | Workload | Use Case | M | Per workload |  | Industry-dependent list | Business capability | Derives workload type and unit | Industry | All engines | Block workload | Proposed
INP-011 | Workload | Demand Value | M | Per workload |  | Numeric with unit | Business volume | Drives capacity |  | RPS/TPS/training/storage | Block workload | Proposed
INP-012 | Workload | Demand Unit | A/D | Per workload |  | Use-case-specific | Demand semantics | Controls conversion | Use case | Capacity | Review if unmapped | Proposed
INP-013 | Workload | Simple/Medium/Complex Mix | M | Per workload |  | Percent, total 100% | Usage profile | Drives weighted token behavior |  | Tokens, model and capacity | Block until 100% | Proposed
INP-014 | Workload | Language Coverage | M | Per workload |  | Governed language profile | Supported languages | Model and token eligibility |  | Model and token engines | Block workload | Proposed
INP-015 | Workload | File Types / Modality | M | Per workload |  | Multi-select | Content type | Model, ingestion and storage |  | Model/storage/ingestion | Block workload | Proposed
INP-016 | Workload | Development Required | M | Per workload | Yes | Yes / No | Environment requirement | Creates Development sizing |  | Dev pools and BOM | Block workload | Proposed
INP-017 | Workload | Production Required | M | Per workload | Yes | Yes / No | Environment requirement | Creates Production sizing |  | Prod pools and BOM | Block workload | Proposed
INP-018 | Workload | Performance Tier | M | Per workload | Standard | Standard / Responsive / Real-Time / Custom | Service target | Derives TTFT/TPOT/latency constraints |  | Candidate eligibility | Block Production if absent | Proposed
INP-019 | Workload | Model Override | O | After recommendation |  | Approved model record | Customer constraint | Allows controlled override | Final recommendation | All downstream outputs | Use recommendation | Proposed
INP-020 | Workload | Override Reason | C | When override supplied |  | Text | Audit justification | Required for governance | Override | Traceability | Reject override | Proposed

## Output Baseline
Initial Output Baseline
Outputs presently approved at source-requirement level.
Output ID | Output | Audience | Environment | Objective | Contents | Readiness Rules | Traceability | Status | Notes
OUT-001 | Model Candidate Matrix | Architect | Per workload | Both | Eligible and rejected models with reasons | Missing critical evidence -> Review | Inputs, rules, catalogs, evidence | Proposed
OUT-002 | Performance-Optimized Model | Executive/Architect | Per workload | Performance | Model, rationale, confidence and assumptions | Must pass validation checkpoint | Full trace | Proposed
OUT-003 | Price-Optimized Model | Executive/Architect | Per workload | Price | Model, rationale, projected compliant cost and assumptions | Must pass validation checkpoint | Full trace | Proposed
OUT-004 | GPU/Infrastructure Candidate Matrix | Architect | Per workload | Both | GPU/server/cloud choices and failed constraints | Only eligible options ranked | Full trace | Proposed
OUT-005 | Development Performance-Optimized BOM | Executive/Procurement | Development | Performance | Compute, storage, network, software and costs | Quote/evidence gates | BOM-line trace | Proposed
OUT-006 | Development Price-Optimized BOM | Executive/Procurement | Development | Price | Lowest-cost compliant Development design | Quote/evidence gates | BOM-line trace | Proposed
OUT-007 | Production Performance-Optimized BOM | Executive/Procurement | Production | Performance | Active, failure reserve, maintenance, DR and shared infrastructure | Architecture/quote gates | BOM-line trace | Proposed
OUT-008 | Production Price-Optimized BOM | Executive/Procurement | Production | Price | Lowest-cost compliant Production design | Architecture/quote gates | BOM-line trace | Proposed
OUT-009 | Executive Financial Summary | Executive | All | Comparison | CAPEX, OPEX, run rate, TCO, cost drivers and readiness | Must reconcile to detailed BOM | Financial trace | Proposed
OUT-010 | Workload-to-Cluster Allocation | Architect | Dev/Prod | Both | Application, workload, cluster, pool, isolation and resource allocation | Compatibility must pass | Allocation trace | Proposed

## Glossary
Requirements Glossary
Controlled terminology used in the register.
Term | Definition | Status | Notes
M | Mandatory user input | Proposed | Must be entered by authorized user.
O | Optional user input | Proposed | May have a governed default.
D | Derived | Proposed | Calculated from other inputs.
A | Automatically retrieved | Proposed | Retrieved from an active governed catalog.
C | Conditional constraint | Proposed | Required only when applicable.
T | Telemetry preferred | Open decision | Telemetry preferred; assisted input fallback.
A/D | Catalog plus derivation | Proposed | Catalog value participates in deterministic calculation.
Performance-Optimized | Highest-performing eligible option under versioned objective | Approved | Eligibility is mandatory before ranking.
Price-Optimized | Lowest-cost eligible deployable option | Approved | Must still satisfy all hard constraints.
Model baseline | Performance and Price model choices after second validation checkpoint | Approved | Precedes GPU selection.
Procurement Ready | All mandatory technical, evidence, price and approval gates pass | Proposed | Exact gate is OD-006.

## Change Log
Register Change Log
Every update to the source baseline must be recorded.
Version | Date | Author / Owner | Change | Reason | Approval Status
0.1 | 2026-09-21 | Product requirements working session | Created first source inventory, requirement baseline, decisions, open decisions, inputs and outputs. | Start controlled rebuild from source requirements. | Draft